## Sheet1
Sample Schedule for Assessment of EE2001/EE3032 Project
Continuous Assessment | Week1 |  |  |  |  | Week2 |  |  |  |  | Week3 |  |  |  |  | Week4 |  |  |  |  | Week5 |  |  |  |  | Week6 |  |  |  |  | Week7 |  |  |  |  | Week8 |  |  |  |  | Week9 |  |  |  |  | Week10 |  |  |  |  | Week11 |  |  |  |  | Week12
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Specification Development | bar: Week2 M to Week2 F
Project scheduling | bar: Week2 M to Week2 F
System Design | bar: Week3 M to Week3 F
Breadboard Prototyping | bar: Week5 M to Week6 F
PCB System Integration | bar: Week7 M to Week8 F
Final demonstration | bar: Week11 M to Week12 F
Project documentation
Legends:
Planned
Float/slack/allowance
Actual